## Form 7 - DFU
FDP Form 7 - 20% COMPONENT OF THE IRA UTILIZATION
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
| REGION: |  | MIMAROPA |  |  | CALENDAR YEAR: | 2024
| PROVINCE: |  | PALAWAN |  |  | QUARTER: | 1
| CITY/MUNICIPALITY: |  | CITY OF PUERTO PRINCESA
Code | Program / Project |  |  |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extension, if any | Remarks
[9 empty] | % of | Total Cost
[9 empty] | Completion | Incurred to Date
ECONOMIC DEVELOPMENT
8918-3(23) | Completion of Kamuning Public Market Site Development (Road, Parking, Sidewalk, and Drainage)
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Other Land Improvements |  |  | Kamuning | 26628000 | 2024-02-22 | 2024-08-19 | 33.27% | 3879312.6 |  | By contract
8918-4(23) | Site Development of Baywalk Public Market (Road, Parking, Sidewalk and Drainage)
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Other Land Improvements |  |  | Matahimik | 34367000 | 2024-02-22 | 2024-11-02 | 1.93% | 5023296.28 |  | By contract
8918-5(23) | Completion of Macarascas Mini City Hall Perimeter Fence
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Other Land Improvements |  |  | Macarascas | 3462221 | 2024-02-22 | 2024-05-21 | 28.47% |  |  | By contract
8918-6(23) | Completion of Irawan Agri-Trading Center Fence
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Other Land Improvements |  |  | Irawan | 6975000 | 2024-02-22 | 2024-07-20 | 0.41% |  |  | By contract
Site Development of Napsan Mini City Hall ( Road, Parking, Sidewalk and Drainage)
8918-8(23) | 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Other Land Improvements |  |  | Napsan | 12453000 | 2024-02-22 | 2024-09-03 | 2.43% |  |  | By contract
Site Development of Macarascas Mini City Hall ( Road, Parking, Sidewalk and Drainage)
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-9(23) |  | Other Land Improvements |  |  | Macarascas | 15000000 | 2024-02-22 | 2024-09-18 | 78.5% |  |  | By contract
Site Development of Salvacion Public Market (Road, Parking, Sidewalk and Drainage)
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-10(23) |  | Other Land Improvements |  |  | Salvacion | 20000000 | 2024-02-22 | 2024-07-20 | 0.1% |  |  | By contract
Construction of Kamuning Public Market Perimeter Fence and Landscape
3.0 Capital Outlay
8918-11(23) |  | Other Land Improvements |  |  | Kamuning | 6069520 | [5 empty] | Unimplemented
Construction of New City Cemetery Phase V
3.0 Capital Outlay
8918-13(23) |  | Other Land Improvements |  |  | Sta. Lourdes | 30000000 | [5 empty] | For implementation
Construction of New Muslim Cemetery Perimeter Fence, Brgy. San Jose
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-14(23) |  | Other Land Improvements |  |  | San Jose | 2334700 |  |  |  | 1403406.4 |  | By admin
Concreting of Road Leading to Balsahan River, Brgy. Iwahig
3.0 Capital Outlay
8918-15(23) |  | Infrastructure Assets - Road Networks |  |  | Iwahig | 13500000 | [5 empty] | For implementation
Concreting of Access Road to Ubaldo Conde High School, Brgy. Manalo
3.0 Capital Outlay
8918-16(23) |  | Infrastructure Assets - Road Networks |  |  | Manalo | 3835000 | [5 empty] | For implementation
Replacemet/Concreting of Manalo Extension (Fernandez to Abrea Road) Phase II, Brgy. Milagrosa
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-17(23) |  | Infrastructure Assets - Road Networks |  |  | Milagrosa | 46067000 | 2024-02-22 | 2024-09-18 | 3.32% |  |  | By contract
Concreting/Completion of Cactus Road with Drainage System, Brgy. Sta. Monica
3.0 Capital Outlay
8918-18(23) |  | Infrastructure Assets - Road Networks |  |  | Sta. Monica | 5539000 | [5 empty] | For implementation
Concreting/Completion of Perimeter Road at Magbanua Elementary School, Brgy. San Pedro
3.0 Capital Outlay
8918-19(23) |  | Infrastructure Assets - Road Networks |  |  | San Pedro | 2992000 | [5 empty] | For implementation
Concreting of Caramuran Extension at Purok El Rancho, Brgy. Sta. Monica
3.0 Capital Outlay
8918-22(23) |  | Infrastructure Assets - Road Networks |  |  | Sta. Monica | 7532000 | [5 empty] | For implementation
Concreting of Road Networks at Medina Relocation Site, Brgy. Sicsican
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-23(23) |  | Infrastructure Assets - Road Networks |  |  | Sicsican | 10000000 | 2024-02-22 | 2024-07-05 | 20.49% | 1465626.31 |  | By contract
Concreting of Arcinas Road with Drainage System beside Provincial PNP Station, Brgy. Tiniguiban
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-24(23) |  | Infrastructure Assets - Road Networks |  |  | Tiniguiban | 13691000 | 2024-02-22 | 2024-11-17 | 2.96% |  |  | By contract
Concreting of Road Network at Engineering/Architecture Building and GSO Warehouse
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-25(23) |  | Infrastructure Assets - Road Networks |  |  | Sta. Monica | 24000000 | 2024-02-22 | 2024-09-18 | 3.35% | 3506191.86 |  | By contract
Concreting of Laban-Buesa Road (Interior Casuy Road), Brgy. Sta. Monica
3.0 Capital Outlay
8918-26(23) |  | Infrastructure Assets - Road Networks |  |  | Sta. Monica | 3150000 | [5 empty] | For implementation
Concreting of Felimon Lagan Road (Interior Hagedorn-Libis Road), Brgy. San Pedro
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-30(23) |  | Infrastructure Assets - Road Networks |  |  | San Pedro | 9884000 | 2024-02-22 | 2024-10-03 | 12.86% |  |  | By contract
Concreting of VISAPA Road 1 with Drainage Syatem, Brgy. Irawan
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-32-a(23) |  | Infrastructure Assets - Road Networks |  |  | Irawan | 10000000 | 2024-02-29 | 2024-07-27 | 0.53% | 8400 |  | By contract
Road Reblocking of Paduga Road (National Highway to Sampaloc Street, Brgy. Sta. Monica)
| 3.0 Capital Outlay | [10 empty] | For implementation
8918-32-b(23) |  | Infrastructure Assets - Road Networks |  |  | Sta. Monica | 10764000 |  |  |  | 1462948.35 |  | By admin
Road Reblocking of Salve Regina Road, Brgy. Tiniguiban
| 3.0 Capital Outlay | [10 empty] | For implementation
8918-32-c(23) |  | Infrastructure Assets - Road Networks |  |  | Tiniguiban | 261500 |  |  |  | 205113.7 |  | By admin
Road Reblocking of Parangue Road, Brgy. Sicsican
| 3.0 Capital Outlay | [10 empty] | For implementation
8918-32-d(23) |  | Infrastructure Assets - Road Networks |  |  | Sicsican | 813500 |  |  |  | 724945.75 |  | By admin
Road Reblocking of Manalo Street (H. Mendoza Street to Fernandez Street)
| 3.0 Capital Outlay | [10 empty] | For implementation
8918-32-e(23) |  | Infrastructure Assets - Road Networks |  |  | Various Brgys. | 9996500 |  |  |  | 9203935.25 |  | By admin
Asphalt Overlay of Burgos Street, Various Barangays
| 3.0 Capital Outlay | [10 empty] | For implementation
8918-32-f(23) |  | Infrastructure Assets - Road Networks |  |  | Various Brgys. | 9265000 |  |  |  | 6835822.52 |  | By admin
Asphalt Overlay of H. Mendoza Street
| 3.0 Capital Outlay | [10 empty] | For implementation
8918-33-a(23) |  | Infrastructure Assets - Road Networks |  |  | Various Brgys. | 10066500 |  |  |  | 7424003.3 |  | By admin
Asphalt Overlay of Palanca Road
| 3.0 Capital Outlay | [10 empty] | For implementation
8918-33-b(23) |  | Infrastructure Assets - Road Networks |  |  | Various Brgys. | 1899000 |  |  |  | 1396013.74 |  | By admin
Asphalt Overlay of E. Valencia Street
| 3.0 Capital Outlay | [10 empty] | For implementation
8918-33-c(23) |  | Infrastructure Assets - Road Networks |  |  | Various Brgys. | 9536500 |  |  |  | 7035224.06 |  | By admin
Asphalt Overlay of City PNP Entrance
| 3.0 Capital Outlay | [10 empty] | For implementation
|  | Infrastructure Assets - Road Networks |  |  | San Pedro | 1664000 |  |  |  | 1569448.01 |  | By admin
8918-33-d(23) | Concreting of Katarungan Road (Runway to Baltan Catholic Church)
3.0 Capital Outlay
|  | Infrastructure Assets - Road Networks |  |  | Various Brgys. | 3470100 | [5 empty] | Unimplemented
8918-33-e(23) | Concreting of Access Road to Martha Ville Sibdivision, Brgy. Irawan
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | Irawan | 10000000 | 2024-02-22 | 2024-05-05 | 10.13% |  |  | By contract
8918-33-f(23) | Concreting of San Juan Road (Libis Road to Kalikasan Homes), Brgy. San Pedro
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | San Pedro | 7406500 | 2024-02-22 | 2024-06-05 | 46.04% |  |  | By contract
8918-33-g(23) | 10% PRDP Counterpart - FMR Town Site, Macarascas to Purok Cabairan, Brgy. Manalo
3.0 Capital Outlay
|  | Infrastructure Assets - Road Networks |  |  | Manalo | 20000000 | [5 empty] | For implementation
8918-33-h(23) | Concreting of Farm-to-Market Road Leading to Bisor Phase II, Brgy. Bacungan
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | Bacungan | 5000000 | 2024-02-22 | 2024-07-20 | 60.68% |  |  | By contract
8918-7(23) | Concreting/Completion of FMR from Purok Anonang to Purok Star Apple (Verosel), Brgy. Sicsican
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | Sicsican | 27369000 | 2024-02-20 | 2024-10-10 | 3.35% | 3995137.87 |  | By contract
8918-12(23) | Concreting of Farm-to-Market Road Phase II, Brgy. Marufinas
3.0 Capital Outlay
|  | Infrastructure Assets - Road Networks |  |  | Marufinas | 10000000 | [5 empty] | Unimplemented
Concreting of Puting Buhangin Farm-to-Market Road, Brgy. Mangingisda
8918-31(23) | 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | Mangingisda | 10000000 | 2024-02-22 | 2024-07-05 | 55.75% | 1477812.08 |  | By contract
Construction of Hanging Bridge at Purok 5, Brgy. Inagawan-Sub Colony
8918-20(23) | 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | Inagawan-Sub | 9250000 | 2024-02-22 | 2025-01-16 | 1.16% |  |  | By contract
Construction of Hanging Bridge at No. 2 at Sitio Tagnaya
8918-21(23) | 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | Concepcion | 15500000 | 2024-02-22 | 2024-08-19 | 19.53% |  |  | By contract
Completion of Busngol RC Box Culvert ( Concreting of Approach and Slope Protection), Brgy. Sta. Lourdes
8918-28(23) | 3.0 Capital Outlay
|  | Infrastructure Assets - Road Networks |  |  | Sta. Lourdes | 7532500 | [5 empty] | Unimplemented
Completion of Sidewalk and Slope Protection at Balayong People's Park
8918-29(23) | 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | Sta. Monica | 7044000 | 2024-02-22 | 2024-05-06 | 13.47% |  |  | By contract
Completion of Sidewalk , Curb and Gutter at Suha Road. Brgy. San Jose
8918-27(23) | 3.0 Capital Outlay | [10 empty] | For implementation
|  | Infrastructure Assets - Road Networks |  |  | San Jose | 3247500 |  |  |  | 189173.79 |  | By admin
Construction of Loading and Unloading Bay along Manalo Street (PNS, PSU-LES, and PP Pilot ES)
3.0 Capital Outlay
|  | Infrastructure Assets - Road Networks |  |  | Various Brgys. | 4780000 | [5 empty] | Unimplemented
8918-1(23)
Construction of Slope Protection at Maoyon Bridge, Brgy. Maoyon
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | Maoyon | 5000000 | 2024-03-02 | 2024-06-29 | 20.14% | 8400 |  | By contract
8918-2(23)
Rehabilitation of Water Supply System, Brgy. Bagong Bayan
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Water Supply System |  |  | Bagong Bayan | 5000000 |  |  |  | 3236068.99 |  | By admin
Development of Level III Water System in Barangay Maoyon and Manalo
3.0 Capital Outlay
|  | Water Supply System |  |  | Various Brgys. | 4000000 | [5 empty] | Unimplemented
Rehabilitation/Improvement of Plaza Quartel (Fence, Gate, Landscape, Public Toilet, Admin Office, Information, Monument and Amphitheater with Stage), Brgy. Liwanag
3.0 Capital Outlay
|  | Parks, Plazas and Monuments |  |  | Liwanag | 15979402 | [5 empty] | Project awarded
Construction of Two-Storey PNP Building , Brgy. Luzviminda
3.0 Capital Outlay
|  | Buildings |  |  | Luzviminda | 25194858 | [5 empty] | Project awarded
Renovation of Old Terminal Building - Offices, Brgy. San Jose
3.0 Capital Outlay
|  | Buildings |  |  | San Jose | 58473159.94 | [5 empty] | Unimplemented
Completion of City Engineering and Architecture Building ( Fixture, Office Furniture)
3.0 Capital Outlay
|  | Buildings |  |  | Sta. Monica | 49618597 | [5 empty] | Project awarded
Construction of Standard Day Care Center, Brgy. Kamuning
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | School Buildings |  |  | Kamuning | 5779474 | 2024-02-22 | 2024-07-20 | 1.06% |  |  | By contract
Construction of Standard Day Care Center, Purok Manturon, Brgy. Cabayuygan
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | School Buildings |  |  | Cabayugan | 6889500 | 2024-02-22 | 2024-07-20 | 12.16% |  |  | By contract
Construction of Standard Day Care Center, Brgy. Manalo
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | School Buildings |  |  | Manalo | 5437195 | 2024-02-22 | 2024-07-20 | 24.17% |  |  | By contract
Construction of Standard Day Care Center, Brgy. Sta. Cruz
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | School Buildings |  |  | Sta. Cruz | 5572294 | 2024-02-22 | 2024-07-20 | 12.45% |  |  | By contract
Completion of Public Market at Brgy. Matahimik
We hereby certify that we have reviewed the contents and hereby attest to | 3.0 Capital Outlay | [10 empty] | Project on-going
the veracity and correctness of the data of information contained in this |  | Markets |  |  | Matahimik | 39606355.06 | 2023-11-22 | 2024-06-18 | 33.01% |  |  | By contract
Construction of Salvacion Public Market Phase II ( Water Supply Drilling, Mechanical and Scaling and Deboning Area)
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Markets |  |  | Salvacion | 4200000 | 2023-12-26 | 2024-03-24 | 54.89% |  |  | By contract
Completion of Multi-Purpose Building , Brgy. Tagumpay
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Markets |  |  | Tagumpay | 3384155 | 2024-02-22 | 2024-05-21 | 26.02% |  |  | By contract
Construction of Buenavista Wharf Extension
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Other Structures |  |  | Buenavista | 10000000 | 2024-02-22 | 2024-07-20 | 53.89% |  |  | By contract
Construction of Bagong Bayan Wharf Extension
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Other Structures |  |  | Bagong Bayan | 10000000 | 2024-02-22 | 2024-07-20 | 15.09% |  |  | By contract
Construction of Covered Gym at Tiniguiban Elementary School, Brgy. Tiniguiban
3.0 Capital Outlay
|  | Other Structures |  |  | Tiniguiban | 9859028 | [5 empty] | Project awarded
Construction of Covered Gym at Employees Village, Brgy. San Jose
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Other Structures |  |  | San Jose | 9859028 | 2024-02-22 | 2024-08-19 | 14.87% |  |  | By contract
Completion of Bus and Jeepney Terminal ( Covered Walk, Fix Louvers, Guardhouse, Tiles, Food Stalls and Gates)
3.0 Capital Outlay
|  | Other Structures |  |  | Irawan | 21500000 | [5 empty] | Project awarded
Completion of GSO Compound ( Cement Storage, Driveway, Fence and Gate), Brgy. Sta. Monica
3.0 Capital Outlay
|  | Other Structures |  |  | Sta. Monica | 16200050 | [5 empty] | Unimplemented
We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
APPROVED:
|  | ENGR. ALBERTO P. JIMENEZ |  | REGINA S. CANTILLO
|  | City Engineer/Vice Chairman |  | City Budget Officer
LUCILO R. BAYRON
City Mayor