## 2019 20% IRA U. 1st Qtr
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
for the 1st Quarter, CY 2019
City of Puerto Princesa
Program/ Project |  | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incured to Date
ECONOMIC SERVICES
ECONOMIC SERVICES
8918-184 | ROAD WIDENING & CONCRETING OF ROAD NETWORKS PHASE I,
(FROM NAT'L. HIGHWAY TO SEASHORE) BGY. INAGAWAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Inagawan | 65850000 | 2019-03-29 | 365 CD |  |  |  | On-going
8918-185 | CONCRETING OF DIAZ ROAD, BGY. MILAGROSA
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Milagrosa | 6549000 | 2019-02-06 | 75 CD | 90% | 970246.27 |  | On-going
8918-169-1 | COMPLETION OF PSU TO RAFOLS ROAD PHASE III, BGY. STA. MONICA
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Sta. Monica | 60000000
8918-186 | CONCRETING OF 4-LANE ACCESS ROAD FROM PUERTO PRINCESA SOUTH
ROAD TO CITY HALL, ROTONDA, BALAYONG PARK, BGY. STA. MONICA
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Sta. Monica | 35000000
8918-187 | CONCRETING OF ACCESS ROAD BETWEEN PSU AND SPORTS COMPLEX
BGY. TINIGUIBAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Tiniguiban | 9208301.87 | [5 empty] | Scheduled for bidding
8918-188 | CONCRETING OF MANTURON ROAD (FROM HIGHWAY TO SATELLITE CLINIC),
BGY. CABAYUGAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Cabayugan | 4569000 | 2019-02-18 | 45 CD | 94% | 684343.96 |  | On-going
8918-189 | CONCRETING OF ACCESS ROAD TO NEW CITY CEMETERY, BGY. STA. LOURDES
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Sta. Lourdes | 11460000 | 2019-03-18 | 90 CD |  | 1718601 |  | On -going
8918-190 | OLANGUAN ROAD DEVELOPMENT PHASE II, BGY. BINDUYAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Binduyan | 2625000 | 2019-02-18 | 60 CD | 25% | 392585.07 |  | On-going
8918-191 | CONCRETING OF CAIMITO ROAD WEST, BGY. SAN JOSE
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. San Jose | 13569000 | 2019-02-06 | 75 CD | 77.65% | 2030728.53 |  | On-going
8918-192 | CONCRETING OF KATIPUSDAN-MITRA ROAD, BGY. TAGBUROS
| 2.0 Capital Outlay | Bgy. Tagburos
| Public Infra - Road Networks | & Bgy. Sta Monica | 19340000 | 2019-02-04 | 90 CD | 13.06% | 2885472.31 |  | On-going
8918-15-1 | CONCRETING OF PABLICO ROAD III, BGY. TINIGUIBAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Tiniguiban | 5459170.25 | 2019-02-06 | 60 CD | 98.02% | 809104.78 |  | On-going
8918-193 | PROPOSE RE-ALIGNMENT OF CONCRETE ROAD WITH SLOPE PROTECTION
AND EMBANKMENT, GOLDEN VALLEY, BGY. SICSICAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Sicsican | 1882776.64 | 2019-02-06 | 50 CD | 42.84% |  |  | On-going
8918-88-1 | CONCRETING OF MACOPA ROAD, EMPLOYEES VILLAGE, BGY. STA. MONICA
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Sta. Monica | 1819600 | 2019-02-18 | 45 CD | 1.53% | 259407.82 |  | On-going
8918-96-1 | CONCRETING OF APITONG ROAD PHASE II, BGY. STA. MONICA
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Sta. Monica | 3236000 | 2019-03-15 | 45 CD |  |  |  | On-going
8918-92-1 | CONCRETING OF EMPLOYEES VILLAGE PHASE II, BGY. SAN JOSE
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. San Jose | 12620000 | 2019-03-18 | 120 CD |  | 1884053.9 |  | On-going
8918-194 | CONCRETING OF ROADS LEADING TO GOVERNMENT CENTERS, BGY. NAPSAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Napsan | 2901700 | [5 empty] | Scheduled for bidding
8918-195 | CONCRETING OF ROADS LEADING TO GOVERNMENT CENTERS,
BGY. LUZVIMINDA
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Luzviminda | 4139400 | [5 empty] | Scheduled for bidding
8918-196 | CONCRETING OF MATIYAGA ROAD (SALVE REGINA), PUROK KAAKBAYAN,
BGY. TINIGUIBAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Tiniguiban | 6041500 | 2019-03-18 | 60 CD |  | 905805.15 |  | On-going
8918-197 | CONCRETING OF TAYLOR ROAD, BGY. SAN PEDRO
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. San Pedro | 4544000 | 2019-02-06 | 45 CD | 76.3% | 673297.43 |  | On-going
8918-198 | CONCRETING OF PALAY (PEO ROAD) BGY. BANCAO-BANCAO
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Bancao-Bancao | 5991000 | 2019-03-19 | 60 CD |  | 896400 |  | On-going
8918-199 | CONCRETING OF TUMBAGA ROAD, BGY. SAN JOSE
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. San Jose | 7760000 | 2019-02-06 | 75 CD |  | 1158322.17 |  | On-going
8918-200 | OPENING OF TAGKURIRING ROAD, BGY. SIMPOCAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Simpocan | 4701854.17
8918-201 | CONSTRUCTION AND INSTALLATION OF ROAD TRAFFIC SIGNAGES
(FOR BUKANG LIWAYWAY-MAKANDRING FMR)
2.0 Capital Outlay
| Other Road Network Facilities | Bgy. Langogan | 296109 | [5 empty] | Scheduled for bidding
8918-202 | CONCRETING OF ROAD TO WHARF & BGY. HALL, BGY. BAGONG BAYAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Bagong Bayan | 1125000
8918-108-1 | CONCRETING OF SAN CARLOS ROAD PHASE II, BGY. BACUNGAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Bacungan | 7500000 | 2019-03-14 | 90 CD |  | 1124227.13 |  | On-going
8918-203 | CONCRETING OF LUZVIMINDA ROAD TO PUROK KAPALARAN,
BGY. LUZVIMINDA
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Luzviminda | 15000000 | 2019-02-18 | 90 CD | 20.76% | 2111128.9 |  | On-going
8918-204 | CONCRETING OF MANGINGISDA ROAD (IGLESIA TO BGY. HALL)
BGY. MANGINGISDA
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Mangingisda | 23883300 | [5 empty] | Scheduled for bidding
8918-205 | CONCRETING OF VILLA TERESA FEEDER ROAD, SITIO MELWANG,
BGY. LUCBUAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Lucbuan | 21672000 | 2019-02-18 | 90 CD | 19.05% | 3161508.57 |  | On-going
8918-206 | CONCRETING OF MANALO TO SEASHORE ROAD, BGY. MANALO
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Manalo | 15000000 | 2019-02-18 | 75 CD | 17.82% | 2247970.54 |  | On-going
8918-207 | CONCRETING OF ROAD TO AGRI-TRADING CENTER, BGY. IRAWAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Irawan | 31885287.14 | 2019-03-20 | 210 CD |  | 4451615.04 |  | On-going
8918-208 | CONCRETING OF GUMAMELA ROAD, BGY. STA. MONICA
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Sta. Monica | 6549500 | 2019-03-06 | 60 CD | 1% | 977662.72 |  | On-going
8918-209 | CONCRETING OF ROAD FROM HIGHWAY TO COVERED COURT,
BGY. CONCEPCION
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Concepcion | 858000 | [5 empty] | Scheduled for bidding
8918-210 | CONCRETING OF BAY VISTA ROAD, BGY. STA. MONICA
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Sta. Monica | 11499853.34 | 2019-02-04 | 75 CD | 26.84% | 1717388.87 |  | On-going
8918-211 | CONCRETING OF BAHINTING ROAD, BGY. SAN MANUEL
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. San Manuel | 10970000 | 2019-03-20 | 90 CD |  | 1586254.82 |  | On-going
8918-212 | CONCRETING OF MACAWILI ROAD, BGY. BANCAO-BANCAO
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Bancao-Bancao | 6844000 | 2019-02-11 | 75 CD | 15% | 1025017.62 |  | On-going
8918-213 | CONCRETING OF PERIMETER ROAD, BGY. INAGAWAN-SUB
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Inagawan-Sub | 19263000 | 2019-03-05 | 90 CD | 1% |  |  | On-going
8918-214 | CONCRETING OF MAOYON ROAD, BGY. MAOYON
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Maoyon | 7367000
8918-215 | CONCRETING OF ROAD FROM HIGHWAY TO PSU, BGY. SAN RAFAEL
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. San Rafael | 7759500 | 2019-02-04 | 75 CD |  | 1159071.38 |  | On-going
8918-216 | CONCRETING OF MARUGADING TO BAYBAY ROAD, BGY. MARUYOGON
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Maruyogon | 10524000 | 2019-03-21 | 75 CD |  |  |  | On-going
8918-217 | CONCRETING OF NATIVE ROAD TO VILLAGE, BGY. SALVACION
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Salvacion | 10929000 | 2019-02-05 | 60 CD | 50% |  |  | On-going
8918-218 | REHABILITATION OF ROAD (SUGOD I AND II) BGY. CABAYUGAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Cabayugan | 1220000
8918-219 | CONCRETING OF ROAD FROM HIGHWAY TO BGY. HALL TO COVERED COURT,
BGY. TANABAG
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Tanabag | 4869200 | 2019-03-06 | 60 CD |  | 722359.92 |  | On-going
8918-220 | CONCRETING OF BAHILE TO HIGH SCHOOL ROAD, BGY. BAHILE
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Bahile | 6537000 | 2019-03-15 | 60 CD |  | 972746.89 |  | On-going
8918-183 | CONCRETING OF LANGONGAN GYM ROAD WITH PARKING AND
DRAINAGE SYSTEM, BGY. LANGOGAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Langogan | 4812756.59 | [5 empty] | Scheduled for bidding
8918-13-2 | CONCRETING OF APAN ROAD PHASE II (Leading to Bgy. Mabuhay Relocation Site),
BGY. SICSICAN
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Sicsican | 9966000 | 2019-02-06 | 60 CD | 21.87% | 1466592.47 |  | On-going
|  | GRAND TOTAL | 525597809 |  |  |  | 37991913.26
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
APPROVED:
REGINA S. CANTILLO
City Budget Officer
LUCILO R. BAYRON
City Mayor