## 2020 20% IRA U. 3rd Qtr
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
for the 3rd Quarter, CY 2020
City of Puerto Princesa
Program/ Project |  | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incured to Date
ECONOMIC SERVICES
8918-202 | CONCRETING OF ROAD TO WHARF & BGY. HALL, BGY. BAGONG BAYAN | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Public Infra - Road Networks | Bgy. Bagong Bayan | 555000
8918-218 | REHABILITATION OF ROAD (SUGOD I AND II), BGY. CABAYUGAN | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Cabayugan | 8808000
8918-222 | CONCRETING OF ROAD FROM CHURCH TO HIGHWAY IN BGY. BACUNGAN | [7 empty] | By Admin PR dated 7/15/2020
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Bacungan | 4121500
8918-225 | CONCRETING OF ROAD AT PUROK PAGKAKAISA BGY. SITE (CENTRO), BGY. BAHILE | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Bahile | 13375000
8918-215-1 | COMPLETION OF PSU ROAD, BGY. SAN RAFAEL | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. San Rafael | 16000000
8918-171-1 | CONCRETING OF BGY. SIMPOKAN ROAD NETWORK PH. II, BGY. SIMPOKAN | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Simpokan | 13000000
8918-233 | CONCRETING OF ROAD GOING TO SABANG BEACH, BGY. KAMUNING | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Kamuning | 9736000
8918-92-2 | CONCRETING OF EMPLOYEES VILLAGE PH. III, BGY. SAN JOSE | [7 empty] | On-going By Admin
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. San Jose | 9943000 | 2020-09-29 | 2021-01-26
8918-156-1 | CONCRETING OF MAHOGANY ROAD PHASE II, SICSICAN | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Sicsican | 1581000
8918-238 | CONCRETING OF TAGBUROS BARANGAY SITE ROAD NETWORK, BGY. TAGBUROS | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Tagburos | 21079000
8918-208-1 | CONCRETING OF GUMAMELA ROAD PHASE II (SOUTH HIGHWAY TO EMPLOYEES VILLAGE), STA. MONICA | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Sta. Monica | 5082500
8918-196-1 | CONCRETING OF MATIYAGA ROAD PHASE II (SALVE REGINA), BGY. TINIGUIBAN | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Tiniguiban | 3883000
8918-239 | CONCRETING OF OLANGUAN ACCESS ROAD, BGY. BINDUYAN | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Binduyan | 6210000
8918-240 | CONCRETING OF PUROK MASUNURIN ROAD TO PUROK KAABAYAN, BGY. TINIGUIBAN | [7 empty] | On-going By Admin
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Tiniguiban | 10647500 | 2020-09-29 | 2021-01-11
8918-241 | CONCRETING OF DOÑA AURORA ROAD WITH DRAINAGE, BGY. STA. MONICA | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Sta. Monica | 14207000
8918-244 | CONCRETING OF INAGAWAN TO NIA FARM TO MARKET ROAD, BGY. INAGAWAN | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Inagawan | 10500000
8918-108-2 | CONCRETING OF SAN CARLOS ROAD PH. III IN BGY. BACUNGAN | [7 empty] | By Admin NTP dated 9/8/2020
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Bacungan | 13616500 |  |  |  | 9138510.65
8918-223 | REHABILITATION OF ROAD GOING TO BISOR IN BGY. BACUNGAN | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Bacungan | 6975500
8918-43-1 | REHABILITATION OF PUROK ILONGO FMR IN BGY. BAHILE | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Bahile | 16090000
8918-224 | REHABILITATION OF PUROK MASAGANA FMR (GABAYAN RD.) IN BGY. BAHILE | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Bahile | 7564000
8918-226 | OPENING AND GRAVELLING OF PUROK MALIGAYA ROAD NETWORKS IN BGY. MACARASCAS | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Macarascas | 2470000
8918-227 | OPENING AND GRAVELLING OF PUROK MASAYA TO MACARASCAS NAT'L. HIGH SCHOOL ROAD | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Macarascas | 10650000
8918-228 | REHABILITATION OF PUROK MAGKAKAISA ROAD, BGY. LUCBUAN | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Lucbuan | 5822500
8918-229 | REHABILITATION OF DIONDONG FMR, BGY. LUCBUAN | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Lucbuan | 3958500
8918-231 | REHABILITATION OF PUROK SALENG TO CANDIS FMR, BGY. BABUYAN | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Babuyan | 7886500
8918-44-2 | REHABILITATION OF ANILAWAN FMR, BGY. BABUYAN | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Babuyan | 8863000
8918-40-1 | CONCRETING OF FMR LEADING TO APLAYA AT SITIO LALAWIGAN, BGY. SIMPOKAN | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Simpokan | 9527000
8918-232 | CONCRETING OF KAMUNING ROAD WITH WIDENING AND DRAINAGE (PH I), BGY. KAMUNING | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Kamuning | 25000000
8918-235 | REHABILITATION OF CEMETERY ROAD, BGY. LUZVIMINDA | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Luzviminda | 8884000
8918-236 | REHABILITATION OF ROAD GOING TO LUZVIMINDA ELEMENTARY SCHOOL, BGY. LUZVIMINDA | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Luzviminda | 4600000
8918-237 | CONCRETING OF SANTAN ROAD AT THE CITY EMPLOYEES VILLAGE, BGY. STA. MONICA | [7 empty] | On- going By Admin
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Sta. Monica | 6457000 | 2020-09-29 | 2020-12-12
8918-243 | REHABILITATION OF ROAD LEADING TO NAPSAN CEMETERY | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Napsan | 4605000
8918-230 | REHABILITATION OF BARANGAY ROADS I,II, AND III FROM ELEMENTARY SCHOOL TO SEASHORE, BGY. SAN RAFAEL | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. San Rafael | 4629500
8918-248 | CONCRETING OF IRAWAN AGRICULTURAL CENTER ROAD NETWORK | [7 empty] | On- going. By Contract
2.0 Capital Outlay
| Infrastructure Assets- Roads | Bgy. Irawan | 58486000 | 2020-08-25 | 2021-04-21 | 0.03% | 8668867.75
8918-249 | CONSTRUCTION OF DOUBLE BARREL RC BOX CULVERT WITH APPROACH PAVEMENT, BGY STA. LOURDES | [7 empty] | By Admin. NTP dated 9/8/2020
2.0 Capital Outlay
| Other Road Network Facilities | Bgy. Sta Lourdes | 5533500 |  |  |  | 2104578.15
8918-250 | CONSTRUCTION OF PUBLIC MARKET FOR KAMUNING OR INAGAWAN | [7 empty] | By Contract ABC dated 9/22/2020
2.0 Capital Outlay
| Markets | Bgy. Kamuning | 60000000
8918-251 | CONSTRUCTION OF PUBLIC MARKET FOR BGY. SALVACION | [7 empty] | By Contract ABC dated 9/22/2020
2.0 Capital Outlay
| Markets | Bgy. Salvacion | 60000000
8918-120-2 | CONSTRUCTION OF NEW CEMETERY PHASE III | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Other Land Improvements | Bgy. Sta. Lourdes | 25000000
8918-246 | COMPLETION OF MAOYON COVERED COURT WITH TOILET | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Other Structures | Bgy. Maoyon | 3500000
HEALTH SERVICES
4918-1 | CONSTRUCTION OF NEW CITY HEALTH MEDICAL COMPLEX PHASE II | [7 empty] | By Contract ABC dated 9/30/2020
2.0 Capital Outlay
| Hospitals and Health Centers | Bgy. Sta. Monica | 90000000
4919-2 | CONSTRUCTION OF SATELLITE CLINIC AT BGY. MACARASCAS | [7 empty] | By Contract ABC dated 9/30/2020
2.0 Capital Outlay
| Hospitals and Health Centers | Bgy. Macarascas | 33505000
4919-3 | CONSTRUCTION OF SATELLITE CLINIC AT BGY. LUZVIMINDA | [7 empty] | By Contract. ABC dated 9/16/2020
2.0 Capital Outlay
| Hospitals and Health Centers | Bgy. Luzviminda | 33505000
4919-4 | CONSTRUCTION OF SATELLITE CLINIC AT BGY. SAN RAFAEL | [7 empty] | By Contract ABC dated 8/22/2020
2.0 Capital Outlay
| Hospitals and Health Centers | Bgy. San Rafael | 33505000
SOCIAL WELFARE SERVICES
7919-1 | CONST. OF 8 UNITS STANDARD DAY CARE CENTERS IN PRIORITY AREAS IN RURAL BARANGAY | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Other Structures |  | 16000000
8918-114-2 | COMPLETION OF BAHAY PAG-ASA FOR CHILDREN IN CONFLICT WITH THE LAW (CICL) FOR GIRLS, BGY. MANGINGISDA | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Buildings - Others | Bgy. Mangingisda | 1003600
8918-114-3 | RENOVATION OF EXISTING BAHAY PAG-ASA FOR CICL BOYS, BGY. MANGINGISDA | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Other Structures | Bgy. Mangingisda | 2244600
8918-115-2 | COMPLETION OF EXISTING GROUP HOMES FOR GIRLS AND BOYS, BGY. MANGINGISDA | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Other Structures | Bgy. Mangingisda | 2070300
|  | GRAND TOTAL | 720680500 |  |  |  | 19911956.55
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
APPROVED:
ENGR. ALBERTO P. JIMENEZ | REGINA S. CANTILLO
City Engineer/Vice Chairman | City Budget Officer
LUCILO R. BAYRON
City Mayor