## Form 7 - DFU
FDP Form 7 - 20% COMPONENT OF THE IRA UTILIZATION
UTILIZATION OF THE 20% OF THE NATIONAL TAX ALLOTMENT
| REGION: |  | MIMAROPA |  |  | CALENDAR YEAR: | 2023
| PROVINCE: |  | PALAWAN |  |  | QUARTER: | 4
| CITY/MUNICIPALITY: |  | CITY OF PUERTO PRINCESA
Code | Program / Project |  |  |  | Location | Total Cost | Date Started | Target Completion | Project Status |  | No. of Extension, if any | Remarks
[9 empty] | % of | Total Cost
[9 empty] | Completion | Incurred to Date
ECONOMIC DEVELOPMENT
8918-3(23) | CONCRETING/COMPLETION OF PAGLAUM TO CEMETERY ROAD, BGY. MANGINGISDA
| 3.0 Capital Outlay | [10 empty] | Project completed
|  | Infrastructure Assets - Road Networks |  |  | Mangingisda | 8952645 | 2023-07-14 | 2023-09-27 | 100% | 8883852.88 |  | (Oct. 11, 2023)
8918-4(23) | CONSTRUCTION OF DRAINAGE SYSTEM AT KALYE CUTE PHASE II, BGY. STA. MONICA
3.0 Capital Outlay
|  | Infrastructure Assets - Drainage and Slope Protection Structures |  |  | Sta. Monica | 11698200 | 2024-01-15 | 2024-02-12 |  | 8431456.27 |  | Project on-going
8918-5(23) | CONCRETING OF KAAKBAYAN ROAD NETWORKS WITH DRAINAGE SYSTEM PHASE II, BGY. TINIGUIBAN
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | Tiniguiban | 35000000 | 2023-07-14 | 2024-05-28 | 26.73% | 12785778.84 |  | By Contract
8918-6(23) | CONCRETING/COMPLETION OF RANCHERO ROAD (DIMALANTA TO RAMPANO), BGY. STA. LOURDES | [10 empty] | For preparation of Notice to Proceed and Contract
3.0 Capital Outlay
|  | Infrastructure Assets - Road Networks |  |  | Sta. Lourdes | 11329650
| CONSTRUCTION OF ENGINEERING AND ARCHITECTURE BUILDING PHASE II, BGY. STA. MONICA | [10 empty] | On-going preparation of Plans and POW
8918-8(23) | 3.0 Capital Outlay
|  | Buildings & Other Structures - Buildings |  |  | Sta. Monica | 85000000
UNDERGROUND CABLING OF BALAYONG PARK CIRCUIT PHASE II, BGY. STA. MONICA
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-9(23) |  | Infrastructure Assets - Power Supply Systems |  |  | Sta. Monica | 13446700 | 2023-09-21 | 2024-03-18 | 38.36% | 5740347.58 |  | By Contract
CONCRETING/COMPLETION OF BUKANG-LIWAYWAY HOA ROAD WITH DRAINAGE SYSTEM, BGY.BANCAO-BANCAO
| 3.0 Capital Outlay | [10 empty] | Project completed
8918-10(23) |  | Infrastructure Assets - Road Networks |  |  | Bancao-Bancao | 9357000 | 2023-07-14 | 2023-09-27 | 100% | 7493369.53 |  | (Dec. 20, 2023)
COMPLETION OF CABAIRAN FOOTBRIDGE, BGY. MANALO
| 3.0 Capital Outlay | [10 empty] | Project completed
8918-11(23) |  | Infrastructure Assets - Road Networks |  |  | Manalo | 4075000 | 2023-06-19 | 2023-12-15 | 100% | 59500 |  | (Nov. 30, 2023)
CONCRETING OF ZABALA ROAD WITH DRAINAGE SYSTEM BESIDE TINIGUIBAN ELEM. SCHOOL, BGY. TINIGUIBAN
| 3.0 Capital Outlay | [10 empty] | Project completed
8918-13(23) |  | Infrastructure Assets - Road Networks |  |  | Tiniguiban | 5442675 | 2023-07-14 | 2023-10-16 | 100% | 5371146.42 |  | (Dec. 4, 2023)
OPENING AND GRAVELLING OF OLD SANTOL ROAD, BGY. SAN JOSE
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-14(23) |  | Infrastructure Assets - Road Networks |  |  | San Jose | 5803135 | 2023-07-08 | 2023-09-06 | 25.86% | 5731576.7 |  | By Admin
CONCRETING OF PADUGA ROAD FROM BAPTIST CHURCH TO REGINO ROAD (PUROK PAGKAKAISA), BGY. STA. MONICA
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-15(23) |  | Infrastructure Assets - Road Networks |  |  | Sta. Monica | 9485805 | 2023-07-14 | 2023-11-25 | 98.4% | 8577857.87 |  | By Contract
CONCRETING OF MANGA ROAD (FULBRIGHT COLLEGE), BGY. SAN JOSE
| 3.0 Capital Outlay | [10 empty] | Project completed
8918-16(23) |  | Infrastructure Assets - Road Networks |  |  | San Jose | 19282620 | 2023-07-13 | 2023-11-24 | 100% | 19173888.73 |  | (Nov. 21, 2023)
SITE DEVELOPMENT OF IRAWAN AGRICULTURAL CENTER PHASE II (ROAD, PARKING, SIDEWALK AND DRAINAGE), BGY. IRAWAN
| 3.0 Capital Outlay | [10 empty] | Project awarded with
8918-17(23) |  | Other Land Improvements |  |  | Irawan | 50000000 | [5 empty] | Notice to Proceed
REPLACEMENT/CONCRETING OF MITRA ROAD (BAKER'S HILL), BGY. STA. MONICA
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-18(23) |  | Infrastructure Assets - Road Networks |  |  | Sta. Monica | 95969000 | 2023-07-10 | 2024-08-17 | 51.88% | 49262254.71 |  | By Contract
CONCRETING OF ACCESS ROAD TO VALDEZTAMON RELOCATION SITE, BGY. SICSICAN
3.0 Capital Outlay
8918-19(23) |  | Infrastructure Assets - Road Networks |  |  | Sicsican | 10843000 | [5 empty] | Project awarded
CONCRETING OF ROAD FROM PUROK KAUNLARAN TO PUROK KATIWASAYAN, BGY. LUZVIMINDA
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-22(23) |  | Infrastructure Assets - Road Networks |  |  | Luzviminda | 24549200 | 2023-07-10 | 2024-01-20 | 85.23% | 16607656.95 |  | By Contract
CONSTRUCTION OF CITY CEMETERY PHASE IV, BGY. STA. LOURDES
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-23(23) |  | Other Land Improvements |  |  | Sta. Lourdes | 65474995.53 | 2023-06-01 | 2024-06-29 | 55.33% | 27440760.17 |  | By Contract
CONSTRUCTION OF HANGING BRIDGE AT SITIO KALAKWASAN, BGY. TANABAG
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-24(23) |  | Infrastructure Assets - Road Networks |  |  | Tanabag | 7687500 | 2023-07-31 | 2024-03-26 | 39.6% | 3610196.17 |  | By Contract
CONSTRUCTION OF HANGING BRIDGE AT SITIO TAGNAYA, BGY. CONCEPCION
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-25(23) |  | Infrastructure Assets - Road Networks |  |  | Concepcion | 7687500 | 2023-07-31 | 2024-03-26 | 44.77% | 3974495.25 |  | By Contract
| CONSTRUCTION OF HANGING BRIDGE AT SITIO MANGGAPIN, BGY. CONCEPCION | [10 empty] | Recommended for termination (hanging bridge unnecessary due to an opened road)
3.0 Capital Outlay
8918-26(23) |  | Infrastructure Assets - Road Networks |  |  | Langogan | 7687500
PRINCESS EULALIA PARK LANDSCAPE AND PARKING, BGY. LIWANAG
| 3.0 Capital Outlay | [10 empty] | Project awarded with
8918-30(23) |  | Other Land Improvements |  |  | Liwanag | 10000000 | [5 empty] | Notice to Proceed
| ROAD REBLOCKING OF T.S.PAREDES ST. (former Abad Santos St.) |  |  |  | Masipag,
| 3.0 Capital Outlay |  |  |  | Maunlad & | [6 empty] | Project on-going
8918-32-a(23) |  | Infrastructure Assets - Road Networks |  |  | Bagong Sikat | 25449457.57 | 2023-05-30 | 2023-12-10 | 22.97% | 16723752.44 |  | By Admin
.
ROAD REBLOCKING OF FUNDADOR ROAD
| 3.0 Capital Outlay | [10 empty] | Project completed
8918-32-b(23) |  | Infrastructure Assets - Road Networks |  |  | San Miguel | 2182953.06 | 2023-07-01 | 2023-07-31 | 100% | 2146383 |  | By Admin
ROAD REBLOCKING OF LOMBOY ROAD
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-32-c(23) |  | Infrastructure Assets - Road Networks |  |  | San Jose | 12187980.57 | 2023-05-30 | 2023-08-27 | 52.87% | 11113441.97 |  | By Admin
ROAD REBLOCKING OF MP ROAD
| 3.0 Capital Outlay | [10 empty] | Project completed
8918-32-d(23) |  | Infrastructure Assets - Road Networks |  |  | San Miguel | 2176825.86 | 2023-07-01 | 2023-07-31 | 100% | 2109507 |  | By Admin
ROAD REBLOCKING OF VALENCIA MANALO TO PAROLA ROAD
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-32-e(23) |  | Infrastructure Assets - Road Networks |  |  | Masipag | 19257342.16 | 2023-05-30 | 2023-10-26 | 31.06% | 12336398.98 |  | By Admin
ROAD REBLOCKING OF LANZANAS, TARABIDAN, BM AND TANGAY ROAD
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-32-f(23) |  | Infrastructure Assets - Road Networks |  |  | San Pedro | 15810414.01 | 2023-05-30 | 2023-09-26 | 33.21% | 12393843 |  | By Admin
ASPHALT OVERLAY OF CARANDANG STREET
| 3.0 Capital Outlay | [10 empty] | Project completed
8918-33-a(23) |  | Infrastructure Assets - Road Networks |  |  | Manggahan | 2067426.53 | 2023-11-20 | 2023-12-02 | 100% | 2041027.58 |  | By Admin
ASPHALT OVERLAY OF CASTRO ROAD
| 3.0 Capital Outlay | [10 empty] | Project on-going
8918-33-b(23) |  | Infrastructure Assets - Road Networks |  |  | San Pedro | 2314066.34 | 2023-12-22 | 2024-01-13 |  | 2264472.23 |  | By Admin
ASPHALT OVERLAY OF LACAO STREET
3.0 Capital Outlay
8918-33-c(23) |  | Infrastructure Assets - Road Networks |  |  | Maningning | 8575573.89 | 2023-05-31 | 2023-09-13 | 100% | 8510833.24 |  | Project completed
ASPHALT OVERLAY W/ GRANULAR BASE OF ENTRANCE AT BATCHING PLANT
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | Sta. Lucia | 1142778.67 | 2023-11-09 | 2023-11-18 |  | 1129341.7 |  | By Admin
8918-33-d(23) | ASPHALT OVERLAY OF P. VICENTE STREET
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | San Miguel | 4957915.39 | 2023-10-09 | 2023-11-08 | 100% | 4927382.25 |  | By Admin
8918-33-e(23) | ASPHALT OVERLAY OF SAN JUAN ROAD
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | San Miguel | 2811497.3 | 2023-12-04 | 2023-12-21 | 78.51% | 2798634.2 |  | By Admin
8918-33-f(23) | ASPHALT OVERLAY OF SOLID ROAD
| 3.0 Capital Outlay | [10 empty] | Project completed
|  | Infrastructure Assets - Road Networks |  |  | San Manuel | 7393596.94 | 2023-08-01 | 2023-09-09 | 100% | 7350342.05 |  | By Admin
8918-33-g(23) | ASPHALT OVERLAY OF TARABIDAN ROAD
| 3.0 Capital Outlay | [10 empty] | Project completed
|  | Infrastructure Assets - Road Networks |  |  | San Manuel | 4357667.18 | 2023-09-11 | 2023-10-07 | 100% | 4319651.3 |  | By Admin
8918-33-h(23) | CONCRETING/COMPLETION OF PARALLEL RD. 3 TO PUROK KAPALARAN W/ RC BOX CULVERT, BGY. LUZVIMINDA
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | Luzviminda | 17218250 | 2023-07-10 | 2023-12-06 | 99.21% | 2899358.81 |  | By Contract
8918-7(23) | OPENING AND GRAVELLING OF FMR FROM PUROK 3 TO MARAMBUHAYA, BGY. KAMUNING
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Infrastructure Assets - Road Networks |  |  | Kamuning | 12230000 | 2023-06-28 | 2023-09-26 | 18.28% | 12181457.4 |  | By Admin
8918-12(23) | SOCIAL DEVELOPMENT
RENOVATION OF SINAGTALA DAY CARE CENTER, BGY. BAGONG SILANG
| 3.0 Capital Outlay | [10 empty] | Project awarded
|  | School Buildings |  |  | Bagong Silang | 518859 | [5 empty] | By Contract
8918-31(23) | SITE DEVELOPMENT OF LUZVIMINDA MINI CITY HALL (ROAD, PARKING, SIDEWALK AND DRAINAGE), BGY. LUZVIMINDA
| 3.0 Capital Outlay | [10 empty] | Project completed
|  | Other Land Improvements |  |  | Luzviminda | 6465000 | 2023-07-10 | 2023-10-07 | 100% | 6374061.44 |  | (Nov. 15, 2023)
8918-20(23) | SITE DEVELOPMENT OF SAN RAFAEL MINI CITY HALL (ROAD, PARKING, SIDEWALK AND DRAINAGE), BGY. SAN RAFAEL
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Other Land Improvements |  |  | San Rafael | 21360000 | 2023-07-17 | 2024-01-12 | 21.61% | 254900 |  | By Contract
8918-21(23) | CONSTRUCTION OF PNP BUILDING AT BGY. MACARASCAS
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Buildings & Other Structures - Buildings |  |  | Macarascas | 25000000 | 2023-09-05 | 2024-05-31 | 10.08% | 4201714.98 |  | By Contract
8918-28(23) | CONSTRUCTION OF PNP BUILDING AT BGY. SAN RAFAEL
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Buildings & Other Structures - Buildings |  |  | San Rafael | 26000000 | 2023-07-10 | 2024-04-04 | 39.68% | 11718424.37 |  | By Contract
8918-29(23) | CONSTRUCTION OF HAZARDOUS/HOSPITAL WASTE FACILITY, BGY. STA. LOURDES | [10 empty] | Updating of POW
3.0 Capital Outlay
|  | Infrastructure Assets - Other Infrastructure Assets |  |  | Sta. Lourdes | 25000000
8918-27(23) | COMPLETION OF DOH SATELLITE CLINIC, BGY. NAPSAN
| 3.0 Capital Outlay | [10 empty] | Project on-going
|  | Hospitals and Health Centers |  |  | Napsan | 10800000 | 2023-07-11 | 2024-01-06 | 72% | 6971743.25 |  | By Contract
| COMPLETION OF SENIOR CITIZEN AND CHILDREN'S PARK WITH MOVABLE PUPPET SHOW STAGE, BGY. STA. MONICA | [10 empty] | For Procurement/ Bidding
3.0 Capital Outlay
8918-1(23) |  | Infrastructure Assets - Parks, Plazas and Monuments |  |  | Sta Monica | 13000000
| COMPLETION OF KAMUNING PUBLIC MARKET (WATER SUPPLY DRILLING, MECHANICAL AND SCALING AND DEBONING ROOF), BRGY. KAMUNING | [10 empty] | Project awarded with
| 3.0 Capital Outlay |  |  |  | Kamuning | 3991784.38 | [5 empty] | Notice to Proceed
8918-2(23)
We hereby certify that we have reviewed the contents and hereby attest to | We hereby certify that we have reviewed the contents and hereby attest to the veracity and correctness of tha data or information contained in this document.
the veracity and correctness of the data of information contained in this
document.
APPROVED:
|  | ENGR. ALBERTO P. JIMENEZ |  | REGINA S. CANTILLO
|  | City Engineer/Vice Chairman |  | City Budget Officer
LUCILO R. BAYRON
City Mayor