## 2021 20% IRA U. 4th Qtr
FDP Form 7 - 20% Component of the IRA Utilization
20% COMPONENT OF THE IRA UTILIZATION
for the 4th Quarter, CY 2021
City of Puerto Princesa
Program/ Project |  | Location | Total Cost | Date Started | Target Completion Date | Project Status |  | No. of Extensions, if any | Remarks
[6 empty] | % of Completion | Total Cost Incured to Date
ECONOMIC SERVICES
8918-6 | CONCRETING OF VILLA ISIDRA ROAD NETWORK, MAUNLAD | [7 empty] | With ABC received by CBO on 9/15/2021
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 8815000
8911-1 | CONSTRUCTION OF PUBLIC TOILET, IRAWAN INTEGRATED AGRICULTURAL CENTER, IRAWAN | [7 empty] | On-going By Contract
2.0 Capital Outlay
| Buildings - Others |  | 5000000 | 2021-09-23 | 2022-05-20 | 1.29%
8911-2 | CONSTRUCTION OF PERIMETER FENCE AT IRAWAN AGRICULTURAL CENTER, IRAWAN | [7 empty] | With ABC received by CBO on 8/24/2021
2.0 Capital Outlay
| Other Land Improvements |  | 10920000
8918-30 | CONCRETING OF CATUMABAL ROAD AT PUROK PAGKAKAISA, LUCBUAN (SB#3) | [7 empty] | With PR dated 12/7 & 9/2021
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 6009000
8918-248-1 | CONCRETING OF IRAWAN AGRICULTURAL CENTER ROAD NETWORK PH. II, IRAWAN | [7 empty] | With ABC received by CBO on 10/20/2021
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 40000000
8918-27 | OPENING AND GRAVELLING OF RAC FMR TO HIGHWAY (CBFM ROAD), SALVACION | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 4312500
8918-28 | CONCRETING OF STA. CRUZ ROAD III TO DAUNGAN FMR. STA. CRUZ | [7 empty] | On-going By Contract
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 9393000 | 2021-10-03 | 2022-01-01 |  | 1388718.18
8918-1 | CONCRETING OF BUKANG-LIWAYWAY HOA ROAD AT PUROK MASIPAG, BANCAO-BANCAO | [7 empty] | With ABC received by CBO on 9/8/2021
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 5250000
8918-2 | CONCRETING OF ROAD FROM PIER ENTRANCE TO BAYWALK, BAGONG PAG-ASA | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 2665000
8918-3 | CONCRETING OF GABUCO ROAD, BAGONG SIKAT | [7 empty] | On-going By Administration
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 4100000 |  |  |  | 585845.5
8918-4 | CONCRETING OF IPIL STREET (RIVERSIDE ROAD), IRAWAN | [7 empty] | On-going By Contract
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 10250000 | 2021-10-06 | 2022-01-03 |  | 1578293.58
8918-161-1 | COMPLETION OF MALIGAYA ROAD (TANGUEGUE ROAD), MANDARAGAT | [7 empty] | Completed. By Administration
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 2187500 | 2021-08-30 | 2021-09-28 | 100% | 1702716
8918-5 | CONCRETING OF PENSYLVANIA ROAD AT PUROK BAKAWAN, MANDARAGAT | [7 empty] | On-going By Administration
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 1837500 | 2021-08-30 | 2021-09-28 | 96.24% | 1135715
8918-7 | CONCRETING OF PIO MANLAVI ROAD, MILAGROSA | [7 empty] | With PR dated 12/6/2021
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 8347500
8918-8 | CONCRETING OF SAN JOSE NEW MARKET BY-PASS ROAD (SOUTH TO NORTH NAT'L. HIGHWAY), SAN JOSE | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 40211000
8918-9 | CONCRETING OF SUHA ROAD WITH DRAINAGE SYSTEM, SAN JOSE | [7 empty] | On-going. By Contract
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 17842500 | 2021-09-23 | 2022-02-19 |  | 2707808.08
8918-11 | CONCRETING OF ROAD LEADING TO EMERALD APLAYA BEACH/MICROTEL, SAN MANUEL | [7 empty] | On-going @56.08% By Contract
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 15050000 | 2021-09-23 | 2022-02-04 | 0.1% | 9330607.33
8918-12 | CONCRETING OF CABIGUEN ROAD (ARMANDO LOPEZ), SAN MIGUEL | [7 empty] | On-going. By Administration
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 9012500 | 2021-09-10 | 2021-11-08 | 70.4% | 3629870.44
8918-13 | CONCRETING OF ROAD GOING TO PUERTO PRINCESA SCIENCE HIGH SCHOOL WITH SIDEWALK AND DRAINAGE SYSTEM, STA. MONICA | [7 empty] | On-going. By Contract
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 17511000 | 2021-09-23 | 2022-02-04 | 0.38% | 2664860.55
8918-14 | CONCRETING OF DIMALANTA TO RANCHERO ROAD, STA. LOURDES | [7 empty] | On-going By Contract
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 14000000 | 2021-10-06 | 2022-02-12 |  | 2132055.83
8918-15 | CONCRETING OF SUBDIVISION ROAD AT PAGKAKAISA RELOCATION SITE, SICSICAN | [7 empty] | On-going @56.97% By Contract
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 10250000 | 2021-10-05 | 2021-12-14 |  | 6466277.21
8918-16 | CONCRETING OF MABUHAY RELOCATION ROAD NETWORK BLOCK 3, SICSICAN | [7 empty] | On-going By Contract
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 7236500 | 2021-11-24 | 2/21/20222 |  | 1074185.08
8918-17 | CONCRETING OF ROAD LEADING TO CITY SLAUGHTERHOUSE WITH SIDEWALK AND DRAINAGE SYSTEM, TAGBUROS | [7 empty] | On-going By Contract
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 20905500 | 2021-09-23 | 2022-02-04 |  | 2664917.74
8918-18 | CONCRETING OF PABLICO ROAD 2, TINIGUIBAN | [7 empty] | Project Completed @100%
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 6877500 | 2021-10-05 | 2021-12-06 |  | 5411732.94
8918-19 | CONCRETING OF BINDUYAN CEMETERY CIRCULATION ROAD, BINDUYAN | [7 empty] | With PR dtd. 9/30/2021
| 2.0 Capital Outlay | [7 empty] | By Administration
| Infrastructure Assets- Roads |  | 4100000
8918-20 | CONCRETING AND WIDENING OF INAGAWAN ROAD WITH SIDEWALK AND DRAINAGE SYSTEM PHASE II, INAGAWAN | [7 empty] | Awarded. For implementation
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 18500000
8918-21 | CONCRETING OF ROAD LEADING TO IWAHIG HERITAGE CENTER, IWAHIG | [7 empty] | On-going. By Admin
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 16681500 | 2021-08-12 | 2022-01-23 | 13.07% | 14827268.1
8918-232-1 | CONCRETING AND WIDENING OF KAMUNING ROAD WITH SIDEWALK AND DRAINAGE SYSTEM PHASE II, KAMUNING | [7 empty] | On-going. By Contract
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 45140000 | 2021-08-02 | 2022-05-13 | 10.57% | 6707801.13
8918-22 | CONCRETING OF ROAD FROM PUROK KAUNLARAN TO MINI CITY HALL, LUZVIMINDA | [7 empty] | On-going. By Contract
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 11719000 | 2021-09-23 | 2022-01-05 | 2.71%
8918-23 | CONCRETING OF PAGLAUM TO CEMETERY ROAD, MANGINGISDA | [7 empty] | With ABC received by CBO on 9/7/2021
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 5850000
8918-25 | CONCRETING OF ROAD LEADING TO UGONG ROCK, TAGABENIT | [7 empty] | With ABC received by CBO on 9/7/2021
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 5850000
8918-254 | CONST. OF BATCHING PLANT- OTHER FACILITIES, STA. LUCIA | [7 empty] | On- going By Administration
2.0 Capital Outlay
| Const. & Heavy Eqpt.- Batching Plant, Concrete |  | 9758432 | 2021-03-10 |  | 39.13% | 7474467.1
8918-10 | CONCRETING OF ROAD GOING TO KUYBA ALMONECA, SITIO MASIKAP, SAN JOSE | [7 empty] | On-going. By Administration
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 4100000 | 2021-09-10 | 2021-11-08 | 94.81%
8918-26 | CONCRETING OF DURANGOL FMR, BGY. INAGAWAN | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 9920000
8919 | CONDUCT OF FEASIBILITY STUDY AND DETAILED ENGINEERING DESIGN FOR PPC FISHPORTS (Main and Satellite) | [7 empty] | On-going. By Contract
1.0 Current Operating Expenditures
| Consultancy Services |  | 33000000 |  |  |  | 4937424
GENERAL PUBLIC SERVICES
1918-1 | CONSTRUCTION OF DORMITORY AT LUZVIMINDA RURAL SERVICE CENTER, LUZVIMINDA | [7 empty] | Awarded. For implementation
2.0 Capital Outlay
| Buildings - Others |  | 10000000
1918-2 | COMPLETION OF MINI CITY HALL (FENCE, GATE, PARKING, LANDSCAPE AND OUTDOOR LIGHTING), LUZVIMINDA | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Other Land Improvements |  | 2500000
1918-3 | COMPLETION OF MINI CITY HALL (FENCE, GATE, PARKING, LANDSCAPE AND OUTDOOR LIGHTING), MACARASCAS | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Other Land Improvements |  | 5000000
1918-4 | COMPLETION OF MINI CITY HALL (FENCE, GATE, PARKING, LANDSCAPE AND OUTDOOR LIGHTING), NAPSAN | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Other Land Improvements |  | 5000000
1918-5 | CONSTRUCTION OF DORMITORY AT SAN RAFAEL RURAL SERVICE CENTER, SAN RAFAEL | [7 empty] | Awarded. For implementation
2.0 Capital Outlay
| Buildings - Others |  | 10000000
1918-7 | CONSTRUCTION OF PHILIPPINE NATIONAL POLICE BUILDING IN BARANGAY NAPSAN | [7 empty] | Temporarily suspended due to
| 2.0 Capital Outlay | [7 empty] | lot boundery discrepancy
| Buildings |  | 22500000 | 2021-09-08 | 2022-06-04 | 1.37%
1918-6 | COMPLETION OF MINI CITY HALL (FENCE, GATE, PARKING, LANDSCAPE AND OUTDOOR LIGHTING), SAN RAFAEL | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Other Land Improvements |  | 2500000
HEALTH SERVICES
4917-1 | RENOVATION/ IMPROVEMENT OF BUENAVISTA SATELLITE CLINIC, BUENAVISTA | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Hospitals and Health Centers |  | 1000000
4917-2 | RENOVATION/ IMPROVEMENT OF INAGAWAN SATELLITE CLINIC, INAGAWAN | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Hospitals and Health Centers |  | 1000000
4917-3 | RENOVATION/ IMPROVEMENT OF SALVACION SATELLITE CLINIC, SALVACION | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Hospitals and Health Centers |  | 1000000
4919-5 | PUBLIC HEALTH EMERGENCY RESPONSE FOR CORONA VIRUS DISEASE - 2019 (COVID-19) PANDEMIC PROGRAM (VACCINATION PROJECT) | [7 empty] | Payment for Astrazeneca vaccines
1.0 Current Operating Expenditures
| Drugs and Medicines Expenses |  | 50062000 |  |  |  | 16257166.25
4919 | PURCHASE OF VACCINES REFRIGERATOR/FREEZER/COLD CHAIN TRANSPORT COOLER AND OTHER ANCILLARY EQUIPMENT | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Other Property, Plant and Equipment |  | 3350000
SOCIAL WELFARE SERVICES
6918-1 | CSWD RESIDENTIAL CARE FACILITIES SITE DEVELOPMENT/COVERED PATHWAYS, MANGINGISDA | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Other Land Improvements |  | 500000
6918-2 | REHABILITATION OF DRAINAGE SYSTEM ALONG CARANDANG STREET, MANGGAHAN | [7 empty] | On-going procurement (BAC)
| 2.0 Capital Outlay | [7 empty] | By Administration
| Drainage and Slope Protection Structures |  | 4620000
6918-3 | CONSTRUCTION OF DRAINAGE SYSTEM (ALONG QUEZON STREET FROM BARANGAY HALL TO JUAN LUNA STREET), MATIYAGA | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Drainage and Slope Protection Structures |  | 1715000
6918-4 | CONSTRUCTION OF DRAINAGE SYSTEM AT EMPLOYEES VILLAGE (CACTUS ROAD), STA. MONICA | [7 empty] | On-going procurement (BAC)
| 2.0 Capital Outlay | [7 empty] | By Administration
| Drainage and Slope Protection Structures |  | 1024000
6918-5 | CONSTRUCTION OF DRAINAGE SYSTEM AT CASTRO ROAD, SAN PEDRO | [7 empty] | On-going procurement (BAC)
| 2.0 Capital Outlay | [7 empty] | By Administration
| Drainage and Slope Protection Structures |  | 2800000
6918-6 | CONSTRUCTION OF DRAINAGE SYSTEM AT FERNANDEZ EXTENSION WITH SIDE WALK, TANGLAW | [7 empty] | On-going procurement (BAC)
| 2.0 Capital Outlay | [7 empty] | By Administration
| Drainage and Slope Protection Structures |  | 3551500
6918-7 | CONSTRUCTION OF DRAINAGE SYSTEM AT PUROK KAAKBAYAN (MARINES COMPOUND), TINIGUIBAN | [7 empty] | On-going. By Contract
2.0 Capital Outlay
| Drainage and Slope Protection Structures |  | 19451000 | 2021-09-14 | 2022-02-10 | 2.87%
6919-1 | INSTALLATION OF PUMP/AERATOR FOR WATERPOD AT BALAYONG PARK, STA. MONICA | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Other Power and Energy Supply Facilities |  | 5000000
6919-2 | DEVELOPMENT OF MINI-PARKS ROTUNDA, STA. MONICA | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Parks, Plazas and Monuments |  | 20000000
6919-3 | INSTALLATION OF UNDERGROUND ELECTRICAL LINE AND POWER SUPPLY, STA. MONICA | [7 empty] | With ABC received by CBO on 8/16/2021
2.0 Capital Outlay
| Other Power and Energy Supply Facilities |  | 28000000
6919-4 | INSTALLATION OF WATER SYSTEM DISTRIBUTION, STA. MONICA | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Water Supply System |  | 3595000
6919-5 | Improvement of Balayong Park Facilities (including the Badminton Courts Building at Balayong Park to used as Temporary Testing Center) | [7 empty] | On-going. By Administration
2.0 Capital Outlay
| Other Structures |  | 10710207.5 | 2021-08-16 | 2021-11-23 | 52.34%
8918-186-1 | COMPLETION OF BALAYONG PARK ROAD NETWORK (SIDEWALK/DRAINAGE SYSTEM), STA. MONICA | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Infrastructure Assets- Roads |  | 20000000
8918-111-2 | COMPLETION OF SPORTS COMPLEX BASKETBALL COURT (LIGHTING, RING, BLEACHERS), STA. MONICA | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Other Structures |  | 6000000
8918-111-3 | COMPLETION OF SPORTS COMPLEX INDOOR COURT (LIGHTING AND BLEACHERS), STA. MONICA | [7 empty] | Not yet implemented
2.0 Capital Outlay
| Other Structures |  | 10000000
| COMPLETION OF SPORTS COMPLEX VOLLEYBALL COURT (LIGHTING AND BLEACHERS), STA. MONICA | [7 empty] | With POW dtd. 8/31/2021 By Admin
2.0 Capital Outlay
| Other Structures |  | 5500000
| GRAND TOTAL |  | 698981139.5 |  |  |  | 92677730.04
We hereby certify that we have reviewed the contents and hereby attest to
the veracity and correctness of the data or information contained in this
document.
APPROVED:
ENGR. ALBERTO P. JIMENEZ | REGINA S. CANTILLO
City Engineer/Vice Chairman | City Budget Officer
LUCILO R. BAYRON
City Mayor
City Management Information Services - "Hindi BUKAS kundi NGAYON!...."